Table of Contents

CR-05 - Goals and Outcomes	2

CR-10 - Racial and Ethnic composition of families assisted	7

CR-15 - Resources and Investments 91.520(a)	8

CR-20 - Affordable Housing 91.520(b)	13

CR-25 - Homeless and Other Special Needs 91.220(d, e); 91.320(d, e); 91.520(c)	15

CR-30 - Public Housing 91.220(h); 91.320(j)	17

CR-35 - Other Actions 91.220(j)-(k); 91.320(i)-(j)	19

CR-40 - Monitoring 91.220 and 91.230	22

CR-45 - CDBG 91.520(c)	24

CR-50 - HOME 24 CFR 91.520(d)	25

CR-58 – Section 3	27

## CR-05 - Goals and Outcomes

Progress the jurisdiction has made in carrying out its strategic plan and its action plan.  91.520(a)

This could be an overview that includes major initiatives and highlights that were proposed and executed throughout the program year.

Under federal regulations at 24 CFR 570, the City of Anniston has prepared the 2024 Consolidated Annual Performance and Evaluation Report (CAPER) covering the period October 1, 2024, through September 30, 2025. This report outlines the City’s progress in implementing projects and activities identified in the Program Year (PY) 2024 Annual Action Plan for the Community Development Block Grant (CDBG) and HOME Investment Partnerships (HOME) programs. These funds, received from the U.S. Department of Housing and Urban Development (HUD), are used to principally benefit low- to moderate-income residents of the City.

The 2024 CAPER evaluates how the City invested its formula allocations from HUD to address affordable housing and community development needs. It also provides a broader assessment of progress made toward the priorities and objectives established in the 2023–2027 Five-Year Consolidated Plan. The 2024 CAPER, along with other relevant documents, is available on the City’s website at: http://www.annistonal.gov/pages/?pageID=56.

The City of Anniston continues to make measurable progress in utilizing CDBG and HOME funds by expanding affordable housing opportunities for low- and moderate-income households, supporting local nonprofit organizations that provide essential services to individuals experiencing homelessness and other vulnerable populations, and investing HOME funds to preserve and sustain affordable rental housing.

During PY 2024, the City focused on the following goals:

- Provide decent and affordable housing and supportive services for low- and moderate-income families.

- Improve public facilities and infrastructure to enhance community livability.

- Eliminate slums and blight to promote neighborhood revitalization.

The City of Anniston received $519,183.00 in CDBG funding and $315,822.59 in HOME funding. The City expended a total of $687,885.88 for the following CDBG-eligible activities: Infrastructure Improvements ($297,798.48), public service activities ($71,585.58), clearance and demolition activities in low mod areas ($198,617.00), housing rehabilitation activities ($12,994.60) and general administration ($106,890.22). The City expended a total of $826,470.45 in HOME funds for the following eligible activities: new construction of affordable rental housing ($181,750.00), First Time Homebuyers ($576,616.42), Tenant-based Rental Assistance ($23,729.02) and planning and administration ($44,375.01).

Comparison of the proposed versus actual outcomes for each outcome measure submitted with the consolidated plan and explain, if applicable, why progress was not made toward meeting goals and objectives.  91.520(g)

Categories, priority levels, funding sources and amounts, outcomes/objectives, goal outcome indicators, units of measure, targets, actual outcomes/outputs, and percentage completed for each of the grantee’s program year goals.

| Goal | Category | Source / Amount | Indicator | Unit of Measure | Expected – Strategic Plan | Actual – Strategic Plan | Percent Complete | Expected – Program Year | Actual – Program Year | Percent Complete |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Expand Affordable Housing Opportunities- New Const | Affordable Housing | CDBG: $ / HOME: $576,616.42 | Homeowner Housing Added | Household Housing Unit | 5 | 5 | 100% | 6 | 6 | 100% |
| Expand Affordable Housing Opportunities- TBRA | Affordable Housing | HOME: $23,729.02 | Tenant-based rental assistance / Rapid Rehousing | Households Assisted | 10 | 10 | 100% | 8 | 27 | 100% |
| Provide Administrative Structure | Planning and administration | CDBG: $106,890.22 HOME: $44,375.01 | Other | Other | 1 | 1 | 100% | 1 | 0 | 100% |
| Public Facility & Infrastructure Improvements | Non-Housing Community Development | CDBG: $ 297,798.48 | Public Facility or Infrastructure Activities other than Low/Moderate Income Housing Benefit | Persons Assisted | 1,565 | 1,565 | 100% | 0 | 1,515 | 100% |
| Public Facility & Infrastructure Improvements | Non-Housing Community Development | CDBG: $ / HOME: $ | Public Facility or Infrastructure Activities for Low/Moderate Income Housing Benefit | Households Assisted | 0 | 0 | 0 | 0 | 0 | 0.00% |
| Public Facility & Infrastructure Improvements | Non-Housing Community Development | CDBG: $198,617.00 | Buildings Demolished | Buildings | 20 | 20 | 100.00% | 20 | 36 | 100% |
| Public Service Emergency Housing | Non-Housing Community Development | CDBG: $ / HOME: $ | Public service activities for Low/Moderate Income Housing Benefit | Households Assisted | 85 | 85 | 100.00% | 50 | 50 | 100.00% |
| Public Service Food Insecurity | Non-Housing Community Development | CDBG: $ / HOME: $ | Public service activities other than Low/Moderate Income Housing Benefit | Persons Assisted | 0 | 0 | 0% | 0 | 0 | 0% |
| Public Service General Services Programs | Non-Housing Community Development | CDBG: $13,986.90 | Other | Other | 5 | 5 | 100% | 5 | 5 | 100% |
| Public Service Healthcare | Non-Housing Community Development | CDBG: $21,931.47 | Public service activities other than Low/Moderate Income Housing Benefit | Persons Assisted | 75 | 75 | 100.00% | 50 | 50 | 100.00% |
| Public Service Youth Services | Non-Housing Community Development | CDBG: $15,897.78 | Public service activities other than Low/Moderate Income Housing Benefit | Persons Assisted | 10 | 10 | 100.00% | 25 | 25 | 100.00% |

Table 1 - Accomplishments – Program Year & Strategic Plan to Date

Assess how the jurisdiction’s use of funds, particularly CDBG, addresses the priorities and specific objectives identified in the plan, giving special attention to the highest priority activities identified.

The City of Anniston's Community Development Department maintains partnerships with local nonprofits providing essential services for low-income households and other City departments to assess progress, provide extensions where necessary, and reallocate unused funds where necessary. The City continues to meet our stated goals and objectives from the Action Plan and the Consolidated Plan. During FY2024, the City accomplished the following activities:

- Demolished 36 vacant and abandoned housing units

- Assisted providers in creating 6 affordable rental housing units

- Employed 5 youth from low-income households for job training and mentorships

- Provided tenant-based rental assistance to 27 low-income households

- Provided new affordable housing to 6 households and acquired 1 affordable rental unit

- Provided financial assistance to St. Michael’s to improve health care services for low-income households.

- Provided financial assistance to Community Enabler Developer for emergency food assistance and utility assistance.

- Provided financial assistance to The Right Place, All Saints for Concern, and Interfaith Ministries for emergency rental subsidies, utility assistance, and operating assistance.

## CR-10 - Racial and Ethnic composition of families assisted

Describe the families assisted (including the racial and ethnic status of families assisted). 91.520(a)

|  | CDBG | HOME |
| --- | --- | --- |
| White | 62 | 2 |
| Black or African American | 70 | 18 |
| Asian | 0 | 0 |
| American Indian or American Native | 0 | 0 |
| Native Hawaiian or Other Pacific Islander | 0 | 0 |

| Total | 132 | 20 |
| --- | --- | --- |

| Hispanic | 3 | 0 |
| --- | --- | --- |
| Not Hispanic | 129 | 20 |

Table 2 – Table of assistance to racial and ethnic populations by source of funds

Narrative

The table above displays the number of beneficiaries by race and ethnicity who were assisted through HUD-funded programs in 2024. The ethnicity totals do not exactly match the total beneficiaries by race, due to differences in self-reporting. These discrepancies may result from refusals to provide data, intake errors, or individuals opting not to disclose their race or ethnicity.

## CR-15 - Resources and Investments 91.520(a)

Identify the resources made available

| Source of Funds | Source | Resources Made Available | Amount Expended During Program Year |
| --- | --- | --- | --- |
| CDBG | public - federal | $513,533 | $687,885.88 |
| HOME | public - federal | $288,403 | $826,470.45 |

Table 3 - Resources Made Available

Narrative

Identify the geographic distribution and location of investments

| Target Area | Planned Percentage of Allocation | Actual Percentage of Allocation | Narrative Description |
| --- | --- | --- | --- |
| Anniston - Citywide | 80% | 0% | CDBG and HOME funds were utilized throughout the City during this CAPER period. |

Table 4 – Identify the geographic distribution and location of investments

Narrative

The City of Anniston expended $687,885.88 in CDBG funds during the program year; this total includes $466,176.31 drawn from CDBG allocations from FY 2019, 2021, 2022, and 2023. The City also expended $826,470.45 in HOME funds, of which $797,630.10 was drawn from prior years’ HOME allocations and HOME program income.

The City allocates CDBG and HOME resources based on geographic regions identified as having the greatest need for affordable housing, thereby directing assistance to communities throughout Anniston and Calhoun County.

Leveraging

Explain how federal funds  leveraged additional resources (private, state and local funds), including a description of how matching requirements were satisfied, as well as how any publicly owned land or property located within the jurisdiction that were used to address the needs identified in the plan.

Although the Community Development Block Grant (CDBG) program does not mandate a matching contribution, CDBG investments are typically leveraged through a variety of private and public resources for the projects carried out in 2024. Sub-recipients receiving CDBG allocations also secured additional funding from federal, state, local, and other sources.

For the HOME Investment Partnerships Program (HOME), the City used HOME funds as gap financing for new construction projects. Developers first identified and secured primary financing sources before HOME allocations were awarded. These HOME funds were then leveraged and matched with private lenders, sponsorships from individuals, churches, clubs, and businesses; funding from the local public housing authority; in-kind

The City was granted a match-reduction waiver by HUD based on criteria of fiscal distress, severe fiscal distress, and a Presidential disaster declaration. Under these determinations, and per 24 CFR § 92.222, a participating jurisdiction that meets both distress criteria is eligible for a 100% reduction of its HOME match requirement for the fiscal year in which the determination is made, and the following fiscal year. As a result, the City of Anniston incurred no matching liability for HOME funds during FY 2024, as reported in HUD’s IDIS Report PR33.

| Fiscal Year Summary – HOME Match |  |
| --- | --- |
| 1. Excess match from prior Federal fiscal year | $0 |
| 2. Match contributed during current Federal fiscal year | $0 |
| 3. Total match available for current Federal fiscal year (Line 1 plus Line 2) | $0 |
| 4. Match liability for current Federal fiscal year | $0 |
| 5. Excess match carried over to next Federal fiscal year (Line 3 minus Line 4) | $0 |

Table 5 – Fiscal Year Summary - HOME Match Report

| Match Contribution for the Federal Fiscal Year |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project No. or Other ID | Date of Contribution | Cash (non-Federal sources) | Foregone Taxes, Fees, Charges | Appraised Land/Real Property | Required Infrastructure | Site Preparation, Construction Materials, Donated labor | Bond Financing | Total Match |
| N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |

Table 6 – Match Contribution for the Federal Fiscal Year

HOME MBE/WBE report

| Program Income – Enter the program amounts for the reporting period |  |  |  |  |
| --- | --- | --- | --- | --- |
| Balance on hand at beginning of reporting period $ | Amount received during reporting period $ | Total amount expended during reporting period $ | Amount expended for TBRA $ | Balance on hand at end of reporting period $ |
| $1,415.10 | $155,346.55 | $136,557.16 | $23,729.02 | $18,789.39 |

Table 7 – Program Income

Minority Business Enterprises and Women Business Enterprises – Indicate the number and dollar value of contracts for HOME projects completed during the reporting period

|  | Total | Minority Business Enterprises |  |  |  | White Non-Hispanic |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Alaskan Native or American Indian | Asian or Pacific Islander | Black Non-Hispanic | Hispanic |  |

| Contracts |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Number | 2 | 0 | 0 | 1 | 0 | 1 |
| Dollar Amount | $555,100 | $0 | $0 | 480,100 | $0 | $75,000 |

| Sub-Contracts |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Number | 0 | 0 | 0 | 0 | 0 | 0 |
| Dollar Amount | $0 | $0 | $0 | $0 | $0 | $0 |

|  | Total | Women Business Enterprises | Male |
| --- | --- | --- | --- |

| Contracts |  |  |  |
| --- | --- | --- | --- |
| Number | 2 | 0 | 2 |
| Dollar Amount | $555,100 | $0 | $555,100 |

| Sub-Contracts |  |  |  |
| --- | --- | --- | --- |
| Number | 0 | 0 | 0 |
| Dollar Amount | $0 | $0 | $0 |

Table 8 - Minority Business and Women Business Enterprises

Minority Owners of Rental Property – Indicate the number of HOME assisted rental property owners and the total amount of HOME funds in these rental properties assisted

|  | Total | Minority Property Owners |  |  |  | White Non-Hispanic |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Alaskan Native or American Indian | Asian or Pacific Islander | Black Non-Hispanic | Hispanic |  |
| Number | 0 | 0 | 0 | 0 | 0 | 0 |
| Dollar Amount | $0 | $0 | $0 | $0 | $0 | $0 |

Table 9 – Minority Owners of Rental Property

Relocation and Real Property Acquisition – Indicate the number of persons displaced, the cost of relocation payments, the number of parcels acquired, and the cost of acquisition

|  | Number | Cost |
| --- | --- | --- |
| Parcels Acquired | 0 | 0 |
| Businesses Displaced | 0 | 0 |
| Nonprofit Organizations Displaced | 0 | 0 |
| Households Temporarily Relocated, not Displaced | 0 | 0 |

| Households Displaced | Total | Minority Property Enterprises |  |  |  | White Non-Hispanic |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Alaskan Native or American Indian | Asian or Pacific Islander | Black Non-Hispanic | Hispanic |  |
| Number | 0 | 0 | 0 | 0 | 0 | 0 |
| Cost | $0 | $0 | $0 | $0 | $0 | $0 |

Table 10 – Relocation and Real Property Acquisition

## CR-20 - Affordable Housing 91.520(b)

Evaluation of the jurisdiction's progress in providing affordable housing, including the number and types of families served, the number of extremely low-income, low-income, moderate-income, and middle-income persons served.

|  | One-Year Goal | Actual |
| --- | --- | --- |
| Number of Homeless households to be provided affordable housing units | 100 | 50 |
| Number of Non-Homeless households to be provided affordable housing units | 200 | 145 |
| Number of Special-Needs households to be provided affordable housing units | 50 | 50 |
| Total | 350 | 245 |

Table 11 – Number of Households

|  | One-Year Goal | Actual |
| --- | --- | --- |
| Number of households supported through Rental Assistance | 30 | 27 |
| Number of households supported through The Production of New Units | 2 | 2 |
| Number of households supported through Rehab of Existing Units | 5 | 5 |
| Number of households supported through Acquisition of Existing Units | 4 | 4 |
| Total | 41 | 38 |

Table 12 – Number of Households Supported

Discuss the difference between goals and outcomes and problems encountered in meeting these goals.

The shortage of quality, affordable housing remains a significant barrier for low-income households in the City. To confront this challenge, the City of Anniston will continue to collaborate closely with nonprofit housing developers, for-profit builders, the Anniston Housing Authority (AHA), and community residents. Through ongoing assessment of need, open dialogue about housing issues, and coordinated planning, the City seeks to identify and implement effective solutions.

By leveraging partnerships, the City aims to foster and preserve decent, safe, and affordable housing for low-income residents — whether through rehabilitation of existing housing stock or construction of new affordable units. These efforts will support long-term housing stability, neighborhood revitalization, and equitable access to housing across Anniston.

Discuss how these outcomes will impact future annual action plans.

The City remains committed to achieving its goal of providing decent, safe, sound, and affordable housing for low- and moderate-income residents. The City does not currently plan to revise its projected future accomplishments, as it expects that, over time, actual outcomes will align with those estimates. Given the present pace of assisted housing units, the City anticipates continuing to meet its five-year goals

Include the number of extremely low-income, low-income, and moderate-income persons served by each activity where information on income by family size is required to determine the eligibility of the activity.

| Number of Households Served | CDBG Actual | HOME Actual |  |
| --- | --- | --- | --- |
| Extremely Low-income | 89 | 27 |
| Low-income | 156 | 7 |
| Moderate-income | 0 | 0 |
| Total | 245 | 34 |

Table 13 – Number of Households Served

## CR-25 - Homeless and Other Special Needs 91.220(d, e); 91.320(d, e); 91.520(c)

Evaluate the jurisdiction’s progress in meeting its specific objectives for reducing and ending homelessness through:

Reaching out to homeless persons (especially unsheltered persons) and assessing their individual needs

The City of Anniston works closely with the Homeless Coalition of Northeast Alabama (HCNEA) and other Continuum of Care members to assess service needs and strengthen coordination among local providers serving homeless individuals, families, and subpopulations. As the designated CoC for Calhoun, Etowah, Cherokee, and DeKalb counties, HCNEA and its partner agencies deliver a broad array of supportive services aimed at preventing, reducing, and ending homelessness.

Through this partnership, the City supports community-wide efforts to provide comprehensive mainstream services accessible to residents of Anniston and surrounding areas. The collaborative network spans non-profits, social service organizations, and government agencies, working together to address the multifaceted needs of those experiencing homelessness.

These organizations offer essential supports such as case management, counseling, life-skills training, financial literacy education, and victim advocacy. Such services equip individuals and families with the tools and stability needed to transition into permanent supportive housing or independent living — and to maintain stable employment and self-sufficiency over the long term.

The ultimate goal of this coordinated effort is to support long-term housing stability, reduce recidivism into homelessness, and promote self-sufficiency among vulnerable individuals and families in the community

Developing housing for homeless individuals is one of the most challenging aspects of affordable housing. Chronically homeless individuals need physical and mental health services and housing, which makes it extremely difficult for local providers to house homeless persons with the assurance that they will receive needed services in a timely and sufficient manner. In 2024, the City of Anniston utilized CDBG funding to assist nonprofits in providing emergency rental assistance and transitional housing to homeless or at-risk homelessness households.

Addressing the emergency shelter and transitional housing needs of homeless persons

The City of Anniston is not itself a direct recipient of ESG funds. Instead, local nonprofit organizations receive ESG funding through the Alabama Department of Economic and Community Affairs (ADECA) to address emergency shelter and transitional housing needs within the City. The City supports efforts to increase housing options and promote self-sufficiency for individuals and families who are homeless or at risk of homelessness. Through this support, emergency housing and supportive services — including for those recently released from institutions — become more accessible to homeless families and individuals in the community.

Helping low-income individuals and families avoid becoming homeless, especially extremely low-income individuals and families and those who are:  likely to become homeless after being discharged from publicly funded institutions and systems of care (such as health care facilities, mental health facilities, foster care and other youth facilities, and corrections programs and institutions);  and,  receiving assistance from public or private agencies that address housing, health, social services, employment, education, or youth needs

Public systems and institutions — such as jails, prisons, hospitals, child-welfare, and mental-health facilities — frequently discharge individuals directly into homelessness. To address this, the City of Anniston partners with HCNEA and other CoC members to coordinate release planning across foster care, health, mental-health, and correctional systems. Through a centralized intake process, HCNEA works to prevent homelessness whenever possible; when prevention isn’t feasible, the goal is to reduce the duration of homelessness via emergency shelter, transitional housing, rapid rehousing, and supportive services — and, where resources permit, transition the most vulnerable individuals and families into permanent housing.

To help families avoid homelessness or recover quickly from a housing crisis, the City provides CDBG public-services funding to local nonprofit providers such as Interfaith Ministries. These funds support services including rent and eviction prevention, temporary housing, utility-disconnection assistance, utility reconnections, and utility security deposits — crucial interventions that help residents stabilize housing, avoid shelter entry, or sustain housing after crisis.

Through these coordinated efforts between the City, HCNEA/CoC partners, and nonprofit service providers, Anniston seeks to mitigate homelessness, provide emergency and transitional housing support, and help individuals and families move toward stable, permanent housing and self-sufficiency.

Helping homeless persons (especially chronically homeless individuals and families, families with children, veterans and their families, and unaccompanied youth) make the transition to permanent housing and independent living, including shortening the period of time that individuals and families experience homelessness, facilitating access for homeless individuals and families to affordable housing units, and preventing individuals and families who were recently homeless from becoming homeless again

The City of Anniston coordinates its homelessness prevention and response efforts through collaboration with local nonprofit organizations. This approach helps prevent individuals and families from becoming homeless, and supports those who are already experiencing housing instability to regain stability — whether by preserving their current housing or securing permanent housing.

## CR-30 - Public Housing 91.220(h); 91.320(j)

Actions taken to address the needs of public housing

The City of Anniston and its consortium partners benefit from four local housing authorities that provide a range of housing and supportive services tailored to community needs. Although the City does not own or operate public housing units, it continues to work closely with these authorities and other partners to expand affordable housing opportunities and address the needs of residents living in public and assisted housing.

In 2024, the City advanced several initiatives in support of these goals. Following HUD’s approval of the City’s HOME Investments Partnerships American Rescue Plan (HOME-ARP) Allocation Plan in August 2023, the City moved forward with implementation activities. The plan dedicates funding toward the development of 13 affordable housing units on Allen Street in partnership with the Anniston Housing Authority’s Housing Development Corporation. This project is currently underway and represents a major step toward increasing the supply of high-quality, affordable units for qualifying populations. Additional HOME-ARP resources support Community Enabler Developer, Inc. in providing rental assistance, security deposits, and utility deposits to help prevent homelessness and stabilize vulnerable households.

The City’s Community Development Department also administers CDBG activities that improve housing conditions, strengthen neighborhoods, and expand economic opportunities for low- to moderate-income residents, including individuals residing in public housing communities. These efforts complement the work of local housing authorities by addressing broader community development needs that impact housing stability and quality of life.

To ensure residents are meaningfully involved in housing and community development decisions, the City maintains a HUD-compliant Citizen Participation Plan. This plan outlines procedures for public engagement and emphasizes inclusive outreach to low- and moderate-income residents, minorities, non-English-speaking individuals, and persons with disabilities.

Through these coordinated strategies and ongoing partnerships, the City of Anniston remains committed to supporting public housing residents, expanding affordable housing options, and improving overall living conditions for households throughout the community.

Actions taken to encourage public housing residents to become more involved in management and participate in homeownership

Public housing residents are encouraged to provide input to their local Public Housing Authorities and are invited to participate in the City and Consortium’s public engagement efforts. The City also promotes Fair Housing awareness by distributing HUD materials and encouraging residents to learn about their rights.

All four Anniston-area PHAs engage residents in the development of Annual Agency Plans and other planning documents and provide meeting space and support to Resident Advisory Boards. PHAs further encourage resident involvement through resident councils, leadership opportunities, and training programs that build skills, support employment, and create pathways to long-term self-sufficiency and homeownership.

Actions taken to provide assistance to troubled PHAs

There are no troubled Public Housing Authorities (PHAs) in the City of Anniston or within any of the other member jurisdictions of the Consortium; therefore no actions were taken.

## CR-35 - Other Actions 91.220(j)-(k); 91.320(i)-(j)

Actions taken to remove or ameliorate the negative effects of public policies that serve as barriers to affordable housing such as land use controls, tax policies affecting land, zoning ordinances, building codes, fees and charges, growth limitations, and policies affecting the return on residential investment. 91.220 (j); 91.320 (i)

The City’s Assessment of Fair Housing identified several barriers to affordable housing, including the presence of racially and ethnically concentrated areas of poverty (R/ECAPs). To expand opportunities in these neighborhoods, the City used CDBG funds to support home repair and rehabilitation within R/ECAP tracts and allocated CDBG and HOME resources for property acquisition and redevelopment consistent with the West Anniston Master Plan. The City also invested in demolishing unsafe and blighted structures in R/ECAPs to improve neighborhood conditions and support future community development.

Actions taken to address obstacles to meeting underserved needs.  91.220(k); 91.320(j)

The City continues to face challenges in meeting underserved needs, primarily due to limited resources and the growing gap between household incomes and local housing costs. Many vulnerable residents—including single parents, elderly individuals, persons with disabilities, and households with limited economic means—struggle to afford even lower-cost market-rate units. These affordability constraints create significant barriers to stable housing and access to services.

To address these obstacles, the City and its community partners leveraged CDBG and HOME resources to support housing preservation and development efforts. These investments helped expand affordable rental options and improve the quality of existing units for low-income households. During the program year, the City used HOME funds to construct new rental housing and rehabilitate existing units, helping to increase the supply of safe, decent, and affordable housing for underserved populations.

Actions taken to reduce lead-based paint hazards. 91.220(k); 91.320(j)

Through its CDBG-funded Homeowner Housing Rehabilitation Program, the City of Anniston conducts mandatory initial inspections by a HUD-certified lead and asbestos inspector for all participating homes. If lead-based paint hazards or asbestos are identified, the homeowner is notified, and appropriate mitigation or abatement measures are required before rehabilitation activities proceed. This process ensures that all rehab projects address potential environmental hazards and protect the health and safety of residents, particularly young children and vulnerable households.

Actions taken to reduce the number of poverty-level families. 91.220(k); 91.320(j)

The City of Anniston worked to reduce the number of poverty-level families by supporting programs that expand employment opportunities, improve economic stability, and provide essential services to low-income households. Through CDBG, CDBG-CV, and HOME resources, the City assisted families in achieving greater independence by funding agencies that offer job training, workforce development, financial counseling, and supportive services.

The City also prioritized services for children and youth from low-income families, recognizing that educational success is a key factor in breaking the cycle of poverty. During the program year, funding was used to provide emergency food assistance, school supplies, and basic healthcare services, helping families meet immediate needs while supporting long-term stability and self-sufficiency.

Actions taken to develop institutional structure. 91.220(k); 91.320(j)

The City of Anniston continued to strengthen its institutional structure for administering the CDBG and HOME programs. As the grantee and administrative agent, the City manages both programs through the Community Development Department, with day-to-day operations overseen by the Community Development Coordinator under the direction of the City Manager.

Program administration is supported through coordinated efforts across multiple City departments, including Finance, Engineering, Public Works, Code Enforcement, and Planning. This interdepartmental collaboration is essential for effective program delivery, timely project implementation, and compliance with federal requirements.

To further enhance capacity, the City also maintains partnerships with experienced Community Development consultants who provide technical assistance, staff training, and support in developing required plans, reports, and regulatory documentation. These combined efforts strengthen the City’s institutional framework and improve its ability to meet the needs of Anniston residents.

Actions taken to enhance coordination between public and private housing and social service agencies. 91.220(k); 91.320(j)

The City of Anniston continued to strengthen coordination among public, private, and nonprofit partners involved in housing and service delivery. This included regular communication and consultation with housing and non-housing service providers, public housing authorities, neighboring jurisdictions, and other public agencies to ensure resources are aligned and services are effectively integrated. The City also supported collaborative efforts by allocating General Fund, federal, and state resources to agencies serving residents within the covered jurisdictions.

Within the HOME program, the City worked closely with its newly identified Community Housing Development Organization (CHDO), Wealth Builders, to support the development and preservation of affordable housing. This partnership expands local development capacity and helps increase the supply of quality, affordable housing for low-income households.

Through these strategies, the City enhanced communication, strengthened service integration, and improved the effectiveness of housing and social service initiatives across the region.

Identify actions taken to overcome the effects of any impediments identified in the jurisdictions analysis of impediments to fair housing choice.  91.520(a)

In its most recent Assessment of Fair Housing (AFH), the City of Anniston identified several impediments to fair housing choice, including the presence of racially or ethnically concentrated areas of poverty (R/ECAPs), aging housing stock, blight, and limited access to quality affordable housing. In response, the City implemented a series of actions to reduce these impediments and expand housing opportunities for residents.

To increase opportunity and improve housing conditions within R/ECAPs, the City allocated CDBG funds to support home repair and rehabilitation activities, helping preserve affordable housing for low-income homeowners. The City also used CDBG and HOME resources for property acquisition and renovation in alignment with the West Anniston Master Plan, supporting strategic redevelopment and increasing the availability of safe, decent housing.

Additionally, the City directed funding toward the demolition of unsafe and blighted structures in R/ECAP neighborhoods to eliminate hazardous conditions, reduce neighborhood decline, and create sites suitable for future housing investments. These coordinated efforts helped advance fair housing goals by improving neighborhood conditions, expanding housing opportunities, and supporting reinvestment in historically underserved communities.

## CR-40 - Monitoring 91.220 and 91.230

Describe the standards and procedures used to monitor activities carried out in furtherance of the plan and used to ensure long-term compliance with requirements of the programs involved, including minority business outreach and the comprehensive planning requirements

Each year, the City of Anniston’s Community Development Department conducts a comprehensive risk analysis to determine which grant-funded activities and subrecipients require monitoring for federal and local compliance. This assessment is completed for every subrecipient receiving funds during the program year. Risk scores are averaged, and any project scoring above the average is selected for onsite monitoring. In addition, all new subrecipients and those not monitored within the previous year are automatically selected, regardless of their risk score.

Following completion of the risk analysis, the City schedules onsite monitoring visits. Monitoring Compliance Reports and results letters are issued within 30 days of each visit. Subrecipients must respond to any findings or concerns within 30 days of receiving their results letter. All issues must be resolved and formally closed by the City for subrecipients to remain eligible for funding in the next application cycle.

During the program year, the City monitored six subrecipients. Monitoring results included one finding, four concerns, and three recommendations. All subrecipients were notified of the deficiencies and have up to 30 days to address the issues. Once corrective actions are completed, the City will review and close all findings and concerns accordingly.

Citizen Participation Plan 91.105(d); 91.115(d)

Describe the efforts to provide citizens with reasonable notice and an opportunity to comment on performance reports.

The City of Anniston’s Citizen Participation Plan complies with HUD requirements at 24 CFR 91.105(b) and outlines the City’s commitment to ensuring meaningful public involvement in all HUD-funded programs. The City has established specific actions to promote participation among residents, with particular emphasis on engaging low- to moderate-income households and individuals who are most affected by housing and community development activities.

A draft of the 2024 CAPER was made available for public review and comment for a 15-day period from Monday, December 15, 2025 through Tuesday, December 30, 2025.  Public notice of the comment period was published in The Anniston Star, the City’s official legal organ. The draft CAPER was posted on the City’s Community Development webpage at www.annistonal.gov in English to ensure broad accessibility.

To further encourage community input, the City notified a wide network of nonprofit and community-based organizations, taking affirmative steps to reach low- to moderate-income residents and other stakeholders. All public notices advised residents with disabilities or those with limited English proficiency to contact the Community Development office to request accommodations. A copy of the published advertisement is included in the appendix.

## CR-45 - CDBG 91.520(c)

Specify the nature of, and reasons for, any changes in the jurisdiction’s program objectives and indications of how the jurisdiction would change its programs as a result of its experiences.

During the program year, the City of Anniston reviewed the effectiveness of its programs and made adjustments to better align activities with identified community needs and implementation challenges. While the City’s overarching goals—expanding access to affordable housing, supporting community services, and improving conditions for low- and moderate-income residents—remained consistent, several refinements were made based on lessons learned and stakeholder feedback.

One key adjustment involved strengthening coordination among partner agencies and improving communication with service providers. The City recognized the need for more frequent engagement, clearer reporting expectations, and better alignment of services to ensure that limited resources were used efficiently and reached the residents most in need. As a result, the City enhanced internal monitoring practices and increased technical assistance to subrecipients to support program compliance and performance.

Does this Jurisdiction have any open Brownfields Economic Development Initiative (BEDI) grants?

The City does not have any open Brownfields Economic Development Initiative (BEDI) grant funds.

[BEDI grantees]  Describe accomplishments and program outcomes during the last year.

Not Applicable

## CR-50 - HOME 24 CFR 91.520(d)

Include the results of on-site inspections of affordable rental housing assisted under the program to determine compliance with housing codes and other applicable regulations. Please list those projects that should have been inspected on-site this program year based upon the schedule in 24 CFR §92.504(d). Indicate which of these were inspected and a summary of issues that were detected during the inspection. For those that were not inspected, please indicate the reason and how you will remedy the situation.

During PY 2024, no existing HOME-assisted rental projects reached a required inspection interval, and no new rental projects were placed in service that would have necessitated an initial on-site inspection in accordance with 24 CFR §92.504(d).

Provide an assessment of the jurisdiction's affirmative marketing actions for HOME units. 24 CFR 91.520(e) and 24 CFR 92.351(a)

According to 24 CFR Part 92.351, the City of Anniston has adopted affirmative marketing procedures and requirements for HOME-assisted housing containing five (5) or more housing units.  The requirements do not apply to families with housing assistance with tenant-based rental assistance provided with HOME funds. These affirmative marketing steps provide information to otherwise eligible persons from all racial, ethnic, and gender groups in the housing market area for housing units purchased, constructed, or rehabilitated under the HOME Program. The City of Anniston will periodically assess its affirmative marketing program to determine its success and make any necessary corrective actions. The assessment of the Affirmative Marketing Procedures will occur at least annually as the City evaluates its housing programs as a part of the preparation of the CAPER.

Refer to IDIS reports to describe the amount and use of program income for projects, including the number of projects and owner and tenant characteristics

Program income on-hand is paid out to projects before entitlement funds for new and existing projects.

Describe other actions taken to foster and maintain affordable housing. 24 CFR 91.220(k) (STATES ONLY: Including the coordination of LIHTC with the development of affordable housing). 24 CFR 91.320(j)

The City of Anniston implemented several actions during the program year to foster and maintain affordable housing for low- and moderate-income residents. The City continued to coordinate with the Housing Authority of the City of Anniston to support the effective use of HUD’s Housing Choice Voucher Program, which expands access to safe and affordable rental units in the private market.

The City also supported programs that help residents remain stably housed, including initiatives that provide basic needs assistance, financial support, and housing-related services for vulnerable households such as seniors, persons with disabilities, and families with limited incomes. These efforts help prevent displacement and promote long-term housing stability.

In addition, Anniston strengthened partnerships with nonprofit organizations, social service agencies, and community-based providers to improve coordination of supportive services that directly influence housing security. By improving access to employment resources, youth services, financial counseling, and other supportive programs, the City worked to increase economic resilience and reduce the barriers that contribute to housing instability.

Through these combined efforts, the City continued to expand opportunities for affordable housing and support households in maintaining safe and stable living environments.

## CR-58 – Section 3

Identify the number of individuals assisted and the types of assistance provided

| Total Labor Hours | CDBG | HOME | ESG | HOPWA | HTF |
| --- | --- | --- | --- | --- | --- |
| Total Number of Activities | 0 | 0 | 0 | 0 | 0 |
| Total Labor Hours | 0 | 0 | 0 | 0 | 0 |
| Total Section 3 Worker Hours | 0 | 0 | 0 | 0 | 0 |
| Total Targeted Section 3 Worker Hours | 0 | 0 | 0 | 0 | 0 |

Table 15 – Total Labor Hours

| Qualitative Efforts - Number of Activities by Program | CDBG | HOME | ESG | HOPWA | HTF |
| --- | --- | --- | --- | --- | --- |
| Outreach efforts to generate job applicants who are Public Housing Targeted Workers | 0 | 0 | 0 | 0 | 0 |
| Outreach efforts to generate job applicants who are Other Funding Targeted Workers. | 0 | 0 | 0 | 0 | 0 |
| Direct, on-the job training (including apprenticeships). | 0 | 0 | 0 | 0 | 0 |
| Indirect training such as arranging for, contracting for, or paying tuition for, off-site training. | 0 | 0 | 0 | 0 | 0 |
| Technical assistance to help Section 3 workers compete for jobs (e.g., resume assistance, coaching). | 0 | 0 | 0 | 0 | 0 |
| Outreach efforts to identify and secure bids from Section 3 business concerns. | 0 | 0 | 0 | 0 | 0 |
| Technical assistance to help Section 3 business concerns understand and bid on contracts. | 0 | 0 | 0 | 0 | 0 |
| Division of contracts into smaller jobs to facilitate participation by Section 3 business concerns. | 0 | 0 | 0 | 0 | 0 |
| Provided or connected residents with assistance in seeking employment including: drafting resumes,preparing for interviews, finding job opportunities, connecting residents to job placement services. | 0 | 0 | 0 | 0 | 0 |
| Held one or more job fairs. | 0 | 0 | 0 | 0 | 0 |
| Provided or connected residents with supportive services that can provide direct services or referrals. | 0 | 0 | 0 | 0 | 0 |
| Provided or connected residents with supportive services that provide one or more of the following: work readiness health screenings, interview clothing, uniforms, test fees, transportation. | 0 | 0 | 0 | 0 | 0 |
| Assisted residents with finding child care. | 0 | 0 | 0 | 0 | 0 |
| Assisted residents to apply for, or attend community college or a four year educational institution. | 0 | 0 | 0 | 0 | 0 |
| Assisted residents to apply for, or attend vocational/technical training. | 0 | 0 | 0 | 0 | 0 |
| Assisted residents to obtain financial literacy training and/or coaching. | 0 | 0 | 0 | 0 | 0 |
| Bonding assistance, guaranties, or other efforts to support viable bids from Section 3 business concerns. | 0 | 0 | 0 | 0 | 0 |
| Provided or connected residents with training on computer use or online technologies. | 0 | 0 | 0 | 0 | 0 |
| Promoting the use of a business registry designed to create opportunities for disadvantaged and small businesses. | 0 | 0 | 0 | 0 | 0 |
| Outreach, engagement, or referrals with the state one-stop system, as designed in Section 121(e)(2) of the Workforce Innovation and Opportunity Act. | 0 | 0 | 0 | 0 | 0 |
| Other. | 0 | 0 | 0 | 0 | 0 |

Table 16 – Qualitative Efforts - Number of Activities by Program

Narrative

During the program year, the City of Anniston did not undertake any Section 3 qualitative efforts across its CDBG, HOME, ESG, or HOPWA programs, as reflected in the activity table. No covered projects met the Section 3 thresholds that would trigger requirements for targeted hiring, training, or contracting activities. As a result, no outreach to Section 3 workers or business concerns, job fairs, training programs, or employment-related services were required or conducted under these funding sources.

Although no Section 3–triggering projects occurred during the reporting period, the City remained committed to compliance with Section 3 regulations. Staff continued to review project scopes, monitor subrecipients, and ensure that any future construction or rehabilitation activities are evaluated for Section 3 applicability. The City also maintains established procedures for reporting, contractor notification, and documentation to ensure readiness to implement Section 3 qualitative or quantitative efforts when applicable.

The City will continue to monitor upcoming projects for Section 3 requirements and will implement outreach, training, or contracting strategies as needed should future activities exceed regulatory thresholds.